## Risk Register
Amma's Cybersecurity Risk Register
Risk ID | Risk Description | Affected Asset | Likelihood | Impact | Risk Score | Controls | Mitigation Plan | Owner | Status
R-001 | Phishing emails targeting employees | Email System | 4 | 4 | 16 | Spam filters, basic awareness training | Enforce strong password policy + enable MFA | IT Administrator | Open
R-002 | Outdated software without patches | Internal Server | 3 | 3 | 9 | Basic patch schedule | Implement automated patch management system | IT Administrator | In Progress
R-003 | Weak physical access controls | Server Room | 1 | 3 | 3 | Keycard access, CCTV | Add biometric scanner for restricted entry | Facilities Manager | Monitoring
R-004 | Employees using unauthorized USB drives, risking malware and data exfiltration | Internal network, sensitive files | 3 | 4 | 12 | Basic antivirus, employee handbook discouraging USB use | Implement USB blocking policy, deploy endpoint security tools | IT Security Lead | In Progress
R-005 | Employees have local ambition rights, increasing the risk of malware installs and misconfigurations | End-user workstations, internal network | 5 | 4 | 20 | Basic antivirus, new hire onboarding checklist | Restrict admin rights, implement role-based access controls (RBAC) | IT Security Lead | Open
R-006 | Employees are not receiving regular security awareness training, increasing the risk of human error | Entire organization, user accounts, sensitive data | 4 | 3 | 12 | New hire orientation includes basic security tips | Implement recurring mandatory security awareness training | HR & IT Security Team | In Progress
R-007 | Users are allowed to create weak passwords, increasing the risk of unauthorized access and credential stuffing attacks | User accounts, internal systems, customer data | 4 | 4 | 16 | Basic login authentifcation, awareness during onboarding | Implement password complexity requirements, enforce MFA, schedule password audits | IT Security Lead | Open
R-008 | Cloud environments are deployed without standardized security configurations, increasing the risk of data breaches due to misconfigurations or unauthorized access | Cloud infrastructure, client data, internal systems | 3 | 5 | 15 | Cloud access controls and logging are partially in place | Implement a Cloud Security Posture Management (CPSM) tool, create baseline configuration standards, train cloud admins | Cloud Architect / Security Analyst | In Progress
R-009 | Current backup process is automated and off-site, but has not been tested for data restoration success | Operational data, system configurations | 1 | 4 | 4 | Daily automated backups to secure c;loud storage, encrpytion in transit and at rest | Schedule regular restoration tests to ensure backup integrity | IT Operations Lead | Monitoring
R-010 | The organization lacks a documented and tested incident response plan, increasing the risk of confusion, reputational damage, and recovery delays during cyber incidents | Critical systems, business continuity, reputation | 3 | 4 | 12 | Security team responds to incidents based on experience and ad-hoc procedures | Develop a formal incident response plan, define roles, test with tabletop excercises | CISO / Security Manager | In Progress
© 2025 Amma K. ¦ Cybersecurity Risk Register – Governance & Compliance

## Legend
Risk Score Levels
Risk Level | Score Range | Colour Indicator
High | 16–25
Medium | 9–15
Low | 1–8
Risk Score Formula | Likelihood x Impact = Risk Score
Likelihood (1–5) | Probability of the risk occuring
Impact (1–5) | Severity of the risk's effect
Example | If Likelihood = 4 and Impact = 5, Risk Score = 20 (High Risk)